## Worksheet
Date | Team Member | Activity Description | Budget Allocated (USD) | Actual Spend (USD) | Variance (USD) | Status
2024-04-01 | John Smith | Weekly stand-up meeting planning | 150 | 145 | 5 | On Track
2024-04-05 | Sarah Lee | Design review session with UX team | 300 | 315 | -15 | Over Budget
2024-04-10 | Mike Johnson | Development sprint kickoff | 800 | 795 | 5 | <On Track
2024-04-15 | Emily Chen | Client feedback integration workshop | 500 | 520 | -20 | Over Budget
2024-04-20 | David Kim | Quality assurance testing phase | 600 | 585 | 15 | On Track
Total Budget Allocated |  |  | $3,350.00 | $3,360.00 | -$10.00 | Overall Status: Slight Overrun