## Worksheet
Date | Team Member | Meeting Purpose | Action Items | Owner | Deadline | Status
2024-04-15 | Jane Smith | Project Kickoff & Goals Alignment | Define project scope, assign roles, set milestones | Jane Smith | 2024-04-20 | Open
2024-04-18 | Michael Chen | Client Feedback Review | Compile client feedback, draft response plan | Maria Garcia | 2024-04-25 | In Progress
2024-04-21 | Lena Patel | Weekly Team Sync | Update progress on sprint goals, share blockers | Lena Patel | 2024-04-28 | Open
2024-04-25 | All Team Members | Q3 Strategy Planning Session | Outline goals, budget, and team structure for Q3 | Jane Smith | 2024-05-10 | Pending Review