## Worksheet
Team Collaboration Daily Planner
Day | Collaboration Goal | Task Assignments | Key Stakeholders | Meeting Schedule | Status (Progress) | Risks & Issues th> | Action Items th>
Monday, April 15 | Align project roadmap with marketing team | Review Q2 goals; draft campaign plan | Marketing Lead, Project Manager | 10:00 AM - 11:00 AM (virtual) | In Progress | Marketing feedback delayed by 24h | Follow up with marketing lead by end of day
Tuesday, April 16 | Conduct sprint planning for development team | Define user stories; assign tasks | Dev Manager, QA Lead | 2:00 PM - 3:30 PM (in-person) | Scheduled | No major blockers identified | Document sprint goals in shared board
Wednesday, April 17 | Share client feedback session results | Prepare summary report; host review meeting | Client Success Lead, UX Designer | 9:00 AM - 10:30 AM (virtual) | Pending | Client requests additional input on features | Request clarification from client by noon
Thursday, April 18 | Coordinate cross-functional design review | Finalize UI mockups; present to stakeholders | Product Owner, Design Director | 3:00 PM - 4:30 PM (hybrid) | In Progress | Design inconsistency in mobile flow | Reconcile design standards with dev team
Friday, April 19 | Finalize project milestones and deliverables | Update timeline; send to leadership | Director of Operations, Finance Lead | 1:00 PM - 2:00 PM (virtual) | Scheduled | No known risks at this stage | Send approved plan to stakeholders by EOD