## Worksheet
Category | Team Member | Assigned Tasks | Estimated Effort (hours) | Actual Effort (hours) | Status | Deadline | Progress (%)
Project Planning | Alex Johnson | Define scope, outline roadmap | 20 | 18 | On Track | 2024-04-15 | 90%
Development | Sam Rivera | Build core features, API integration | 60 | 45 | On Track | 2024-05-30 | 75%
Testing & QA | Taylor Kim | Unit & integration testing | 30 | 20 | Behind Schedule | 2024-05-15 | 67%
Documentation | Jordan Lee | User guides, technical docs | 15 | 10 | Behind Schedule | 2024-04-30 | 60%
Deployment | Morgan Wu | Staging & production rollout | 10 | 5 | On Track | 2024-06-10 | 50%
Total Estimated Effort |  |  |  | 135 | Total Actual Effort |  | 108