## Worksheet
Task | Owner | Due Date | Status | Progress (%) | Team Allocation (Hours) | Remaining Debt (Hours)
Design team workflow process | Jane Smith | 2024-04-15 | In Progress | 65% | 16 | 8
Develop collaboration dashboard | Michael Lee | 2024-05-01 | Pending | 0% | 24 | 24
Implement real-time sync features | Alice Chen | 2024-05-15 | Not Started | 0% | 32 | 32
Conduct team retrospection meeting | Team Lead | 2024-04-30 | Completed | 100% | 4 | 0