## Worksheet
Category | Description | Assigned Team Member | Target Goal | Current Progress | Next Step / Action Item | Due Date
Communication Plan | Define weekly check-in meetings and communication channels. | Sarah Johnson | Establish bi-weekly syncs by end of month. | 80% complete | Schedule first meeting on Monday. | 2024-04-15
Shared Workspaces | Set up collaborative tools (e.g., Notion, Google Workspace). | David Chen | All team members have access by April 20. | 60% complete | Finalize access permissions. | 2024-04-20
Task Assignment System | Implement a shared task management system (e.g., Trello). | Maria Lopez | All tasks visible and assigned by April 10. | 40% complete | Complete onboarding for team members. | 2024-04-10
Conflict Resolution Protocol | Develop a clear process for resolving team conflicts. | James Reed | Protocol approved and shared by April 30. | 0% complete | Draft document and collect feedback. | 2024-04-30