## Worksheet
Date | Team Member | Task Assigned | Status | Progress (%) | Budget Allocated ($) | Actual Spend ($) | Variance ($) | Owner | Next Action
2023-10-01 | Alex Johnson | Market Analysis Report | In Progress | 65% | 5,000.00 | 3,250.00 | +1,750.00 | Samantha Lee | Complete draft by Oct 15
2023-10-05 | Jordan Martinez | Client Workshop Planning | Completed | 100% | 3,500.00 | 3,475.00 | 25 | Taylor Reed | Share summary with stakeholders
2023-10-10 | Mia Thompson | Budget Review Meeting | Scheduled | 0% | 2,000.00 | - | - | Jordan Martinez | Prepare agenda by Oct 8
2023-10-15 | Sam Carter | Resource Allocation Plan | In Progress | 40% | 6,000.00 | 2,450.00 | +3,550.00 | Mia Thompson | Finalize by Oct 22
2023-10-20 | Elena Rodriguez | Q4 Financial Forecast | Pending Approval | 25% | 8,000.00 | 1,800.00 | +6,200.00 | Sam Carter | Submit for review by Oct 25
Total Tasks: |  |  |  | 20% | $24,500.00 | $11,925.00 | $12,575.00 | Summary of Financial Performance & Collaboration Status