## Worksheet
Task | Start Date | End Date | Duration (Days) | Assignee | Progress (%) | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Team Lead | 100 | Completed
Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | Product Owner | 85 | In Progress
Design Phase (UI/UX) | 2024-03-26 | 2024-04-10 | 15 | UX Designer | 70 | In Progress
Development Sprint 1 | 2024-04-11 | 2024-04-25 | 15 | Development Team | 60 | In Progress
Testing & QA Phase | 2024-04-26 | 2024-05-15 | 20 | QA Manager | 30 | Planned
Final Review & Feedback | 2024-05-16 | 2024-05-20 | 5 | Team Lead & PO | 0 | Not Started