## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Alex Johnson | Completed
Team Onboarding & Roles Assignment | 2024-03-02 | 2024-03-05 | 4 | Maria Lopez | In Progress
Requirements Gathering Workshop | 2024-03-06 | 2024-03-10 | 5 | David Kim | Planned
Design Phase – UI/UX Prototypes | 2024-03-11 | 2024-03-25 | 15 | Sophie Chen | Scheduled
Development Sprint 1 | 2024-03-26 | 2024-04-05 | 10 | Team A | Not Started
QA Testing & Bug Resolution | 2024-04-06 | 2024-04-15 | 10 | James Reed | Planned
Stakeholder Review & Feedback | 2024-04-16 | 2024-04-18 | 3 | Lena Patel | Scheduled
Final Deployment & Go-Live | 2024-04-19 | 2024-04-19 | 1 | Team B | Not Started