## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-01-01 | 2024-01-03 | 3 | Project Management Team | Completed
Quarterly Strategy Planning | 2024-01-10 | 2024-01-15 | 6 | Strategy & Innovation Team | In Progress
Team Building Workshop | 2024-02-15 | 2024-02-18 | 4 | HR & Operations Team | Planned
Product Development Sprint 1 | 2024-03-01 | 2024-03-31 | 31 | Development Team A | In Progress
UX & Design Review Meeting | 2024-04-10 | 2024-04-15 | 6 | Design & UX Team | Scheduled
Cross-Team Integration Planning | 2024-05-01 | 2024-05-15 | 15 | Integration Steering Committee | Not Started
End-of-Year Team Retrospective | 2024-12-10 | 2024-12-13 | 4 | All Teams | Planned