## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analysts
UI/UX Design Phase | 2024-03-16 | 2024-04-10 | 25 | Design Team
Development Phase (Phase 1) | 2024-04-11 | 2024-05-30 | 51 | Development Team
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | QA Team
User Training Session | 2024-07-01 | 2024-07-05 | 5 | Training Officer
Project Closure & Review | 2024-07-06 | 2024-07-10 | 5 | Project Manager