## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Project Manager | Completed
Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | Product Owner & UX Team | In Progress
Design Phase (Wireframes) | 2024-03-26 | 2024-04-05 | 10 | Design Team | Planned
Development Phase (Frontend) | 2024-04-06 | 2024-05-15 | 40 | Frontend Developers | Not Started
Development Phase (Backend) | 2024-04-06 | 2024-05-31 | 56 | Backend Developers | Not Started
Testing & Quality Assurance | 2024-06-01 | 2024-06-30 | 30 | QA Team | Planned
User Training Sessions | 2024-07-01 | 2024-07-15 | 15 | Training Team | Not Started
Project Review & Go-Live | 2024-07-16 | 2024-07-16 | 1 | Project Manager & Stakeholders | Planned