## Worksheet
Task | Start Date | End Date | Duration | Responsible Team | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 day | Project Management Team | Completed
Requirement Gathering | 2024-04-02 | 2024-04-15 | 14 days | Product Team & Clients | In Progress
Design Phase | 2024-04-16 | 2024-05-10 | 35 days | Design Team | Planned
Development Phase (Phase 1) | 2024-05-11 | 2024-06-30 | 60 days | Engineering Team | Not Started
Testing & QA Review | 2024-07-01 | 2024-07-31 | 31 days | QA Team & Devs | Not Started
Client Review & Feedback | 2024-08-01 | 2024-08-15 | 15 days | Client & Project Team | Planned
Final Deployment & Launch | 2024-08-16 | 2024-08-31 | 16 days | Operations & Dev Team | Not Started