## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Team Lead | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Product Owner | In Progress
Design Phase | 2024-03-16 | 2024-03-31 | 16 | UI/UX Designer | Planned
Development Start | 2024-04-01 | 2024-05-15 | 56 | Development Team | Not Started
Testing & QA Review | 2024-05-16 | 2024-06-10 | 35 | QA Manager | Not Started
Deployment & Go-Live | 2024-06-11 | 2024-06-15 | 5 | Operations Team | Not Started