## Worksheet
Task | Start Date | End Date | Duration (Days) | Assignee | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Maria Lopez | Completed
Team Onboarding & Tool Setup | 2024-04-02 | 2024-04-10 | 9 | David Chen | In Progress
Requirements Gathering Workshop | 2024-04-11 | 2024-04-15 | 5 | Sofia Patel | Planned
Wireframing & Design Review | 2024-04-16 | 2024-04-25 | 10 | James Reed | Scheduled
Development Sprint 1 | 2024-04-26 | 2024-05-10 | 15 | Team A | Not Started
QA Testing & Bug Fixing | 2024-05-11 | 2024-05-30 | 20 | Lena Kim | Planned
Final Review & Deployment | 2024-06-01 | 2024-06-05 | 5 | Team B | Scheduled