## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Product Owner | In Progress
Design Phase | 2024-03-16 | 2024-04-05 | 21 | UI/UX Team | Not Started
Development Phase (Phase 1) | 2024-04-06 | 2024-05-10 | 35 | Engineering Team | Planned
Testing & Quality Assurance | 2024-05-11 | 2024-06-15 | 35 | QA Team | Not Started
Final Review & Deployment | 2024-06-16 | 2024-06-30 | 15 | Project Manager & Engineering Team | Not Started