## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Team Member | Status | Dependencies | Progress (%) | Milestones
T001 | Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | J. Smith | Completed | - | 100 | Kickoff
T002 | Define Project Scope & Objectives | 2024-04-02 | 2024-04-10 | 9 | A. Johnson | In Progress | T001 | 65 | -
T003 | Team Role & Responsibility Assignment | 2024-04-11 | 2024-04-15 | 5 | L. Chen | Not Started | T002 | 0 | -
T004 | Develop Collaboration Framework | 2024-04-16 | 2024-05-15 | 30 | M. Patel | Planned | T003 | 25 | Framework Finalized
T005 | Weekly Team Sync Meetings | 2024-04-17 | 2024-11-30 | 238 | All Team Members | Ongoing | T004, T006 | 95 | -
T006 | Feedback & Iterative Review Cycles | 2024-05-01 | 2024-11-30 | 238 | S. Williams | Planned | T005, T007 | 15 | -
T007 | Finalize Collaboration Strategy & Handoff | 2024-12-01 | 2024-12-15 | 15 | R. Kim | Not Started | T006 | 0 | Final Handoff