## Worksheet
Task | Start Date | End Date | Duration | Responsible Member | Status | Dependencies
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 day | Team Lead | Completed | None
Requirements Gathering | 2024-04-02 | 2024-04-10 | 9 days | Product Manager | In Progress | Kickoff Meeting
Design Phase | 2024-04-11 | 2024-04-25 | 15 days | UI/UX Designer | Planned | Requirements Gathering
Development Phase (Phase 1) | 2024-04-26 | 2024-05-15 | 21 days | Software Developers | Not Started | Design Phase
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 days | QA Engineer | Not Started | Development Phase (Phase 1)
Deployment & Launch | 2024-06-01 | 2024-06-05 | 5 days | DevOps Team | Not Started | Testing & Quality Assurance