## Worksheet
Task | Start Date | End Date | Duration (Days) | Budget (USD) | Resource Allocation | Status
Project Kickoff & Team Setup | 2024-03-01 | 2024-03-05 | 5 | 15,000 | Project Manager, HR Lead | On Track
Requirements Gathering Workshop | 2024-03-06 | 2024-03-15 | 10 | 25,000 | Product Owner, UX Designer | On Track
Financial Modeling & Budget Approval | 2024-03-16 | 2024-03-25 | 10 | 35,000 | Finance Director, CFO | Approved
Team Training & Tools Onboarding | 2024-03-26 | 2024-04-05 | 10 | 18,500 | IT Support, Training Lead | In Progress
Quarterly Financial Review Meeting | 2024-04-06 | 2024-04-10 | 5 | 5,000 | Finance Team | Planned