## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Team Lead | Completed
Define Project Scope | 2024-03-16 | 2024-03-20 | 5 | Project Manager | In Progress
Design Wireframes | 2024-03-21 | 2024-03-28 | 8 | UI/UX Designer | Planned
Develop Backend API | 2024-03-29 | 2024-04-15 | 18 | Backend Engineer | Not Started
Frontend Implementation | 2024-04-16 | 2024-05-10 | 35 | Frontend Developer | Not Started
Testing & QA Review | 2024-05-11 | 2024-05-25 | 15 | QA Team | Not Started
Project Review & Launch | 2024-05-26 | 2024-05-31 | 6 | Team Lead | Planned