## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Project Management Team | Completed
Requirement Gathering & Analysis | 2024-03-16 | 2024-03-28 | 13 | Business Analysts & Stakeholders | In Progress
UI/UX Design Phase | 2024-03-29 | 2024-04-15 | 18 | Design Team | Planned
Development Phase (Phase 1) | 2024-04-16 | 2024-05-10 | 35 | Engineering Team | Scheduled
QA Testing & Bug Fixing | 2024-05-11 | 2024-05-31 | 21 | Quality Assurance Team | Not Started
Final Review & Deployment | 2024-06-01 | 2024-06-15 | 15 | Project Management & IT Ops | Not Started