## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Team Member(s)
T-001 | Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager, Lead Designer | In Progress
T-002 | Define Team Roles & Responsibilities2024-03-02 | 2024-03-15 | 14 | HR, Operations Lead, Project Manager | Pending Review
T-003 | Requirement Gathering Workshop | 2024-03-16 | 2024-03-25 | 10 | Product Owner, UX Designer, QA Lead | Scheduled
T-004 | Wireframe Design Phase2024-03-26 | 2024-04-15 | 30 | UI/UX Team, Product Owner | In Progress
T-005 | User Testing & Feedback Loop2024-04-16 | 2024-05-10 | 35 | QA Team, User Researcher, Product Owner | Pending Start
T-006 | Development Sprint 12024-05-11 | 2024-06-15 | 45 | Software Developers, DevOps Engineer | Scheduled
T-007 | Development Sprint 22024-06-16 | 2024-07-15 | 45 | Software Developers, QA Lead | Pending Approval
T-008 | Final Review & Deployment Planning2024-07-16 | 2024-07-31 | 15 | Project Manager, DevOps Lead, Security Officer | In Review
T-009 | Stakeholder Presentation & Demo Day2024-08-01 | 2024-08-15 | 15 | Marketing, Sales Lead, Project Manager | Scheduled
T-010 | Post-Mortem & Lessons Learned Session2024-08-16 | 2024-08-31 | 15 | All Team Members, HR Representative | Pending Approval
T-011 | Team Building & Retrospective Activity2024-09-01 | 2024-09-30 | 30 | HR, Team Leads, Mentors | Scheduled
T-012 | Quarterly Performance Review (Q3)2024-10-01 | 2024-10-31 | 30 | Management, Team Leads, Finance Officer | Pending Initiation
T-013 | End-of-Year Celebration Planning2024-11-01 | 2024-12-05 | 45 | HR, Team Leads, Office Admins | Pending Start
T-014 | Team Goal Setting for Q4 20242024-12-06 | 2025-01-15 | 30 | All Team Members, Project Manager | In Planning
T-015 | Team Innovation Workshop (Q4)2025-01-16 | 2025-01-31 | 15 | Creative Team, Product Manager, UX Lead | Scheduled
T-016 | Annual Training & Skill Development Plan2025-02-01 | 2025-03-31 | 60 | HR, Department Heads, Mentors | Pending Approval
T-017 | Cross-Functional Planning Session (Q2)2025-04-01 | 2025-04-30 | 30 | All Departments, Project Manager, Ops Lead | Pending Initiation
T-018 | Team Performance Evaluation (Q2)2025-05-01 | 2025-06-30 | 60 | All Team Members, HR Manager, Leadership Team | In Progress
T-019 | Team Retreat & Vision Alignment (Q3)2025-07-01 | 2025-07-15 | 15 | All Team Members, Executive Sponsor, HR Lead | Scheduled
T-020 | Year-End Planning & Future Roadmap Discussion2025-08-01 | 2025-08-31 | 31 | All Team Members, Executive Board, Strategy Office | In Review
T-021 | Team Recognition & Appreciation Event2025-09-01 | 2025-09-30 | 30 | All Employees, HR, Leadership Team | Scheduled
T-022 | Next Year's Project Scoping Workshop (Q1 2026)2025-10-01 | 2025-11-30 | 60 | All Departments, Product Director, Strategy Lead | Pending Approval
T-023 | Team Wellness & Mental Health Check-In (Q4 2025)2025-11-01 | 2025-11-30 | 30 | HR, Employee Services, Wellness Coordinator | Scheduled
T-024 | Closing Meeting for 2025 Project Cycle2025-12-01 | 2025-12-31 | 30 | All Team Members, Leadership, Finance Office | In Progress
Generated from a Multi-Page Gantt Chart Template – Team Collaboration Purpose ¦ Version: v1.2 ¦ Exported as Excel-compatible HTML