## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Business Analysts | In Progress
Design Phase (UI/UX) | 2024-03-16 | 2024-04-05 | 21 | Design Team | Planned
Development Phase (Frontend) | 2024-04-06 | 2024-05-15 | 41 | Frontend Developers | Scheduled
Development Phase (Backend) | 2024-04-06 | 2024-05-15 | 41 | Backend Developers | Scheduled
Testing & QA Phase | 2024-05-16 | 2024-06-10 | 35 | QA Team | Not Started
Deployment & Go-Live | 2024-06-11 | 2024-06-15 | 5 | DevOps Team | Planned
Post-Launch Review | 2024-06-16 | 2024-06-17 | 2 | Project Manager & Team | Not Started