## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Alex Johnson | Completed
Define Project Scope | 2024-04-02 | 2024-04-05 | 4 | Maria Lopez | In Progress
Team Onboarding | 2024-04-06 | 2024-04-10 | 5 | David Kim | Planned
Design Phase Workshop | 2024-04-11 | 2024-04-15 | 5 | Sophia Patel | Scheduled
Development Sprint 1 | 2024-04-16 | 2024-04-25 | 10 | Team A | Not Started
Review & Feedback Session | 2024-04-26 | 2024-04-30 | 5 | James Reed | Planned
Final Project Delivery | 2024-05-01 | 2024-05-03 | 3 | All Team Members | Not Started