## Worksheet
Task ID | Task Name | Start Date | End Date th> | Duration (Days) | Status | Responsible Team Member th>
T101 | Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Completed | Jane Smith
T102 | <Market Research Phase | 2024-03-16 | 2024-03-31 | 16 | In Progress | Marcus Lee
T103 | Design Concept Finalization | 2024-04-01 | 2024-04-15 | 15 | Pending | Sarah Kim
T104 | Development Sprint 1 | 2024-04-16 | 2024-05-10 | 35 | In Progress | Alex Johnson
T105 | Quality Assurance Testing | 2024-05-11 | 2024-05-30 | 20 | Pending | Lena Brown
T106 | Final Review & Deployment Planning | 2024-06-01 | 2024-06-15 | 15 | Pending | Jamal White