## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-04-02 | 2024-04-15 | 14 | Product Owner & UX Team | In Progress
Design Phase (Wireframes) | 2024-04-16 | 2024-04-25 | 10 | Design Team | Planned
Development Phase (Frontend) | 2024-04-26 | 2024-05-31 | 36 | Frontend Team | Not Started
Development Phase (Backend) | 2024-05-01 | 2024-06-15 | 66 | Backend Team | Not Started
Testing & QA Review | 2024-06-16 | 2024-07-15 | 31 | QA Team | Planned
User Training & Onboarding | 2024-07-16 | 2024-07-31 | 16 | Support Team | Not Started
Final Project Review & Sign-Off | 2024-08-01 | 2024-08-03 | 3 | Project Manager & Stakeholders | Planned