## Worksheet
Task | Start Date | End Date | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | Team Lead | Completed
Requirements Gathering | 2024-03-04 | 2024-03-15 | Product Manager | In Progress
UI/UX Design Phase | 2024-03-18 | 2024-04-05 | Design Team | Planned
Development Phase (Phase 1) | 2024-04-08 | 2024-05-10 | Engineering Team | Not Started
Testing & Quality Assurance | 2024-05-15 | 2024-06-01 | QA Team | Planned
User Training & Launch | 2024-06-05 | 2024-06-15 | Support Team | Not Started