## Worksheet
Team Collaboration Gantt Chart - Report Version
Generated on: April 5, 2024 ¦ Format: Excel Compatible HTML Table
Task | Start Date | End Date | Responsible Person | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | Jane Doe | Completed
Team Role Assignment | 2024-04-022024-04-05John Smith | In Progress
Weekly Sync Planning | 2024-04-08 | 2024-06-30 | Alice Brown
Feedback Collection Phase | 2024-05-152024-05-31Mike Taylor | Planned
Final Review & Reporting | 2024-06-152024-06-18Sarah Lee | Pending