## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Team Lead
Requirement Gathering | 2024-04-02 | 2024-04-10 | 9 | Product Manager
Design Phase | 2024-04-11 | 2024-04-25 | 15 | UI/UX Designer
Development Start | 2024-04-26 | 2024-05-15 | 21 | Development Team
Testing & Quality Assurance | 2024-05-16 | 2024-05-31 | 16 | QA Team
Project Review & Delivery | 2024-06-01 | 2024-06-03 | 3 | Team Lead