## Worksheet
Task | Start Date | End Date | Responsible | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | Sarah Johnson | Completed
Market Research | 2024-04-02 | 2024-04-10 | David Lee | In Progress
Product Design Draft | 2024-04-11 | 2024-04-25 | Maria Chen | Planned
Development Phase Start | 2024-04-26 | 2024-05-31 | John Wilson | Not Started
User Testing & Feedback | 2024-06-01 | 2024-06-15 | Lisa Park | Scheduled
Final Review & Launch | 2024-06-16 | 2024-06-30 | Team Lead | Not Started