## Worksheet
Task | Start Date | End Date | Duration | Responsible | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 day | Alex Johnson | 100%
Market Research & Analysis | 2024-03-02 | 2024-03-15 | 14 days | Sarah Lee | 85%
Product Design Phase | 2024-03-16 | 2024-04-15 | 30 days | Jordan Kim | 60%
Prototype Development | 2024-04-16 | 2024-05-10 | 35 days | Morgan Reed | 40%
User Testing & Feedback | 2024-05-11 | 2024-05-31 | 21 days | Taylor Wu | 75%
Final Product Review & Launch | 2024-06-01 | 2024-06-30 | 30 days | Team Leadership | 5%