## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Management Team | Completed
Requirement Gathering | 2024-03-02 | 2024-03-15 | 14 | Product & UX Team | In Progress
Design Phase | 2024-03-16 | 2024-04-10 | 35 | Design Team | Planned
Development Sprint 1 | 2024-04-11 | 2024-05-03 | 33 | Engineering Team | Not Started
Testing & QA Review | 2024-05-04 | 2024-05-31 | 28 | QA & Testing Team | Scheduled
Final Review & Deployment | 2024-06-01 | 2024-06-15 | 15 | All Teams (Collaborative) | Not Started