## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-15 | 2024-03-15 | 1 | Team Lead | Completed
Requirements Gathering | 2024-03-16 | 2024-03-25 | 10 | Product Manager | In Progress
Design Phase (UI/UX) | 2024-03-26 | 2024-04-10 | 15 | Design Team | Not Started
Development Phase (Frontend) | 2024-04-11 | 2024-05-15 | 35 | Frontend Developers | Planned
Development Phase (Backend) | 2024-04-11 | 2024-05-30 | 50 | Backend Developers | Planned
Testing & Quality Assurance | 2024-06-01 | 2024-06-15 | 15 | QA Team | Not Started
User Training & Documentation | 2024-06-16 | 2024-06-30 | 15 | Support Team | Not Started
Project Review & Launch | 2024-07-01 | 2024-07-05 | 5 | Team Leadership | Planned