## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Project Manager | Completed
Team Alignment Workshop | 2024-03-04 | 2024-03-05 | 2 | Team Leads | In Progress
Design Phase Review | 2024-03-10 | 2024-03-15 | 6 | Design Team | Planned
Development Sprint 1 | 2024-03-18 | 2024-03-25 | 8 | Development Team | Scheduled
QA Testing & Feedback Loop | 2024-03-28 | 2024-04-03 | 6 | QA Team | Pending
Final Review & Deployment | 2024-04-05 | 2024-04-10 | 6 | Project Manager & Dev Team | Not Started