## Worksheet
Task | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress (%)
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | John Doe | Completed | 100
Requirements Gathering | 2024-03-02 | 2024-03-15 | 14 | Jane Smith | In Progress | 65
Design Phase | 2024-03-16 | 2024-04-10 | 35 | Alex Johnson | Not Started | 0
Development (Phase 1) | 2024-04-11 | 2024-05-30 | 60 | Sarah Lee | Not Started | 0
Testing & QA | 2024-06-01 | 2024-06-30 | 30 | Michael Brown | Not Started | 0
Deployment & Go-Live | 2024-07-01 | 2024-07-15 | 15 | Emily Davis | Not Started | 0