## Worksheet
Date | Team Meeting Time | Agenda Items | Action Items | Responsible Person | Status (✅/❌) | Notes
2024-04-05 | 10:00 AM | Project timeline review | Update sprint plan for week 3 | Alex Morgan | ✅ | All team members confirmed attendance.
2024-04-06 | 14:30 PM | Feedback collection from clients | Compile feedback into summary report | Sara Chen | ❌ | Client feedback delayed due to email issues.
2024-04-07 | 09:15 AM | Weekly performance check-in | Share progress updates with stakeholders | Jamal Reed | ✅ | All goals on track; minor delays in QA.
2024-04-08 | 16:00 PM | Tooling update discussion | Evaluate new collaboration software | Tina Patel | ❌ | Need additional input from IT department.
2024-04-09 | 11:30 AM | Problem-solving session on task delays | Identify root causes and assign solutions | David Kim | ✅ | Root cause identified; action plan agreed.