## Worksheet
Date | Meeting Time (HH:MM) | Agenda Item | Key Decisions | Action Items (Owner) | Status Check-in th>
2024-04-01 | 10:00 | Project Roadmap Review | Approve Q2 milestones | Update roadmap doc (Alex) | Sent to stakeholders
2024-04-05 | 14:30 | Team Feedback Session | Identified communication gaps in sprint planning | Create feedback form (Sam) | Form drafted and shared
2024-04-10 | 16:00 | Tool Selection Discussion | Select new project management tool | Natalie to evaluate options (Natalie) | Final decision scheduled for April 15
2024-04-15 | 09:30 | Sprint Planning Meeting | Set sprint goals and assign tasks | All tasks assigned to team leads (Team Leads) | All tasks visible in Jira
2024-04-18 | 15:00 | Weekly Progress Review | Pending task completion rate at 75% | Follow-up with lagging team members (Jordan) | Improved response time in follow-ups
2024-04-22 | 13:00 | Conflict Resolution Workshop | Made clear escalation process for disagreements | Create team agreement document (Elena) | Document shared and signed by all members
Date | Meeting Time (HH:MM) | Agenda Item | Key Decisions | Action Items (Owner) | Status Check-in th>
2024-04-25 | 11:00 | Retrospective Session (Sprint 3) | Suggested better timeboxing for stand-ups | Implement new stand-up structure (Ryan) | New structure piloted this week
2024-04-29 | 14:00 | Onboarding Process Review | Simplified onboarding checklist added to wiki | Create new onboarding guide (Mia) | Guide approved and shared with new hires
2024-05-03 | 16:30 | Performance Feedback Discussion | Scheduled monthly peer reviews | Set up calendar for peer review meetings (Chloe) | Review calendar confirmed with team leads
2024-05-07 | 10:30 | Demo & Feedback Meeting | Product demo received positive feedback from users | Update user stories based on input (Team) | User feedback integrated into backlog
2024-05-10 | 15:00 | Team Goals Alignment Meeting | All team members aligned on Q2 goals | Share updated goal chart (David) | All members signed off on shared vision
2024-05-14 | 13:15 | Cross-Functional Sync | Determined dependencies between product and engineering teams | Create dependency map (Tina) | Map shared with both departments for review