## Worksheet
Task | Owner | Due Date | Status | Collaboration Notes
Project Kickoff Meeting | Emma Thompson | 2023-10-05 | Completed | Meeting notes shared via Teams. All team members attended.
Design Wireframes Finalized | Liam Chen | <><2023-10-12In Progress | Feedback from UX team is pending. Review scheduled for 10/15.
Develop Backend API | Sophia Patel | 2023-10-25 | Pending | Waiting on database schema approval from DB team.
Client Presentation Draft | Jordan Lee | 2023-10-30 | Not Started | Initial draft to be prepared after feedback from design team.
Post-Meeting Follow-Up | All Team Members | 2023-10-08 | Completed | Follow-up tasks distributed via email and Slack.