## Worksheet
Item ID | Team Member | Role | Assigned Task | Status | Last Updated | Notes
INV-001 | Alex Johnson | Project Lead | Define project scope and objectives | Completed | 2024-04-05 | Scope approved by stakeholders
INV-002 | Sara Kim | Developer | Develop API endpoints | In Progress | 2024-04-06 | Integration with authentication module pending
INV-003 | James Reed | QA Analyst | Conduct unit testing | Pending | 2024-04-07 | Waiting for developer to finalize code
INV-004 | Linda Wu | UX Designer | Finalize user interface mockups | Completed | 2024-04-04 | Feedback from product team included in revision