## Worksheet
Item | Team Member | Assigned Date | Status | Due Date | Progress (%) | Notes
Project Kickoff Meeting | John Smith | 2024-03-15 | Completed | 2024-03-15 | 100% | All team members confirmed attendance and objectives agreed.
Resource Allocation Plan | Sarah Lee | 2024-03-18 | On Track | 2024-04-10 | 75% | Waiting on approval from IT department.
Weekly Sync Schedule | David Chen | 2024-03-20 | Completed | 2024-03-20 | 100% | Scheduled every Monday at 10:30 AM.
Risk Assessment Report | Lisa Wong | 2024-03-25 | Pending Review | 2024-04-05 | 40% | Initial draft completed; awaiting manager feedback.
Team Training Modules | Michael Torres | 2024-03-28 | Planned | 2024-05-15 | 0% | No training materials available yet.