## Worksheet
Month | Team Member | Role | Assigned Tasks | Task Status | Completion Date | Notes/Comments
January 2024 | Anna Smith | Project Manager | Lead project planning, resource allocation | Completed | 2024-01-31 | All milestones aligned with Q1 goals.
January 2024 | James Lee | Developer | API integration testing | In Progress | 2024-02-15 | Testing on staging environment; awaiting QA review.
January 2024 | Sarah Chen | Designer | UI/UX wireframe finalization | Completed | 2024-01-28 | User feedback incorporated; approved for dev.
February 2024 | Anna Smith | Project Manager | Team sprint planning meeting | Completed | 2024-02-05 | All team members present and goals set.
February 2024 | James Lee | Developer | Backend service optimization | In Progress | 2024-03-10 | Performance improvements underway.
February 2024 | Sarah Chen | Designer | Mobile app layout review | Pending Review | 2024-02-18 | Waiting for product owner feedback.