## Worksheet
Date | Team Member | Activity | Duration (mins) | Objective | Outcome | Notes
2024-04-05 | Alex Johnson | Daily Stand-up Meeting | 15 | Review progress and blockers | All tasks on track; minor delay in API testing
2024-04-05 | Sam Rivera | Code Review Session | 30 | Improve code quality in frontend module | Implemented consistent naming convention; 2 bugs caught early | Feedback provided to design team for UI alignment
2024-04-05 | Mia Chen | User Feedback Workshop | 45 | Gather input on new feature flow | Identified key pain points in registration process | Proposed redesign for mobile users; added to sprint backlog
2024-04-06 | Jordan Lee | Project Planning Call | 25 | Outline next week’s deliverables | Defined clear milestones; assigned ownership per task | Follow-up meeting scheduled for Thursday at 10 AM
2024-04-06 | Taylor Brooks | Cross-functional Sync | 35 | Align marketing and development timelines | Updated launch timeline to include QA phase on Day 7 | Marketing team to provide campaign assets by EOD