## Worksheet
Task | Responsible Team Member | Start Date | End Date | Status | Priority | Estimated Effort (hrs)
Project Kickoff Meeting | Team Lead | 2024-04-01 | 2024-04-01 | Completed | High | 2.5
Requirement Gathering Workshop | Product Owner | 2024-04-03 | 2024-04-05 | In Progress | High | 8
Design Review Session | UX Designer | 2024-04-10 | 2024-04-12 | Planned | Medium | 6.5
Development Sprint 1 | Frontend & Backend Team | 2024-04-15 | 2024-04-25 | In Progress | High | 40
QA Testing Phase | QA Team | 2024-05-01 | 2024-05-10 | Planned | Medium | 15