## Worksheet
Month | Team Member | Assigned Task | Budget Allocation (USD) | Status | Progress (%) | Notes
January | Emma Thompson | Project Kickoff Meeting Planning | 2,500 | On Track | 90% | Completed initial agenda and team alignment.
January | James Reed | User Requirement Gathering | 3,200 | In Progress | 65% | Meeting scheduled for 15th; feedback pending.
February | Lena Ortiz | UI/UX Design Development | 4,800 | On Track | 85% | Prototype approved by product lead.
February | Marcus Chen | Backend API Integration | 5,000 | At Risk | 40% | Dependency delay from third-party service.
March | Sofia Patel | Testing & Quality Assurance | 3,500 | On Track | <75% | Test cases finalized; regression testing in progress.
Total Budget Allocation: |  |  | $21,000