## Worksheet
Week | Team Activity | Assigned Members | Budget Allocation (USD) | Actual Spend (USD) | Variance (USD) | Status
Week 1 | Project Kickoff Meeting & Planning | Team A, PM, UX Designer | 2000 | 1950 | 50 | On Track
Week 2 | Weekly Standups & Sprint Planning | Team B, Scrum Master | 1500 | <1475 | 25 | On Track
Week 3 | Feature Development (User Auth) | Team C, Backend Devs, QA | 3000 | 2920 | 80 | On Track
Week 4 | Design Review & Feedback Session | Design Team, Product Owner | 1200 | 1180 | 20 | On Track
Week 5 | Performance Testing & Bug Fixes | QA Team, DevOps | 2500 | 2480 | 20 | On Track
Week 6 | Client Presentation & Feedback | Team D, Sales Lead | 1800 | 1790 | 10 | On Track
Team Collaboration Monthly Budget – Weekly Breakdown