## Worksheet
Month | Team Objective | Key Activities | Ownership | Deadlines | Status | Notes/Action Items
January | Establish core team workflows and onboarding processes | Conduct team meetings, document SOPs, set up communication channels | Project Manager & Team Leads | Jan 31 | In Progress | Finalize SOPs by end of month; share with all members.
February | Improve cross-departmental collaboration | Host quarterly sync-ups, implement shared dashboards | Operations Lead & IT Team | Feb 28 | Planned | Ensure access to real-time data tools for all departments.
March | Launch team performance review cycle | Develop feedback forms, schedule quarterly reviews | HR & Team Leads | Mar 31 | Scheduled | Include peer feedback and development goals.
April | Enhance remote collaboration tools | Train on new software, optimize meeting workflows | IT & Training Manager | Apr 30 | In Progress | Complete mandatory training for all team members.
May | Identify and resolve collaboration bottlenecks | Analyze meeting efficiency, reduce email volume | Team Leads & Analytics Lead | May 30 | Pending | Present findings and recommended changes in team review.