## Worksheet
Order ID | Team Member | Task Description | Assigned Date | Due Date | Status | Progress (%) | Collaboration Notes
ORD-2024-001 | Jane Smith | Finalize project roadmap for Q3 | 2024-03-15 | 2024-04-15 | In Progress | 65% | Moving forward with design inputs from UX team.
ORD-2024-002 | Mike Johnson | Conduct user interviews for new feature | 2024-03-18 | 2024-04-10 | Pending Approval | 30% | Waiting on manager sign-off to proceed.
ORD-2024-003 | Sarah Lee | Develop API documentation | 2024-03-202024-04-15 | On Hold | 10% | Waiting for backend team to finalize endpoints.
ORD-2024-004 | Daniel Kim | Organize weekly sync meeting agenda | 2024-03-17 | 2024-03-31 | Completed | 100% | All team members provided feedback and approved.