## Worksheet
Order ID | Team Member | Task Description | Assigned Date | Due Date | Status | Priority | Progress (%) | Collaboration Notes
ORD-2024-TM-001 | Alex Johnson | Finalize quarterly project roadmap | 03/15/2024 | 04/10/2024 | In Progress | High | 65% | Team meeting scheduled for 03/20 to review milestones.
ORD-2024-TM-002 | Samantha Lee | Conduct cross-departmental strategy session | 03/18/2024 | 04/05/2024 | Pending | Medium | 0% | Waiting on IT team to provide access.
ORD-2024-TM-003 | David Chen | Develop new onboarding workflow | 03/20/2024 | 04/15/2024 | Completed | High | 100% | Workflow approved by HR and Operations.
ORD-2024-TM-004 | Jordan Park | Coordinate team sync with Product Lead | 03/25/2024 | 04/03/2024 | In Progress | Medium | 40% | First draft sent on 03/27. Feedback pending.
ORD-2024-TM-005 | Taylor Reed | Draft team performance review framework | 04/01/2024 | 04/18/2024 | Not Started | High | 0% | Initial outline drafted by Finance team.