## Worksheet
Task | Assignee | Due Date | Status | Priority | Estimated Effort (hrs) | Progress (%)
Project Kickoff Meeting | Alex Morgan | 2024-04-01 | Completed | High | 4 | 100%
Requirement Gathering | Jamie Lee | 2024-04-10 | In Progress | High | 8 | 65%
UI/UX Design Approval | Taylor Reed | 2024-04-15 | Pending | Medium | 6 | 0%
Development Sprint Planning | Jordan Kim | 2024-04-20 | Not Started | High | 12 | 0%
Testing Phase Initiation | Morgan Smith | 2024-05-05 | Not Started | Medium | 10 | 0%