## Worksheet
Category | Team Member | Assigned Task | Due Date | Status | Progress (%)
Project Planning | Alex Morgan | Define project scope and goals | 2024-03-15 | Completed | 100%
Design Phase | Jordan Lee | Create wireframes and UI mockups | 2024-03-25 | In Progress | 75%
Development | Samira Patel | Build core application features | 2024-04-10 | Not Started | 0%
Testing & QA | Tomas Ruiz | Conduct unit and integration tests | 2024-04-20 | Planned | 0%
Client Review & Feedback | All Team | Present final deliverables to client | 2024-05-05 | Scheduled | 0%